## Projects
Project | Developer | Township(s) | County | Acreage | MW (AC if known) | Stage/Status | Approving body & date | Local ordinance status | Litigation / organized opposition | Priority? | Opposition group(s) | Source URLs
45th Parallel Solar | RWE Solar Development (45th Parallel Solar LLC); build-transfer agreement to Consumers Energy approved by MPSC in U-21816 on Nov 6 2025 | Hayes | Otsego | ~1,000+ (RWE site); 2,025 per lawsuit coverage | 200 MWac | Construction per RWE (COD end-2027); county PC 'RWE Solar Project Update' agenda items May & Sept 2026 | Otsego County Planning Commission SUP PZSU24-017, Feb 3 2025 (county zoning) | County zoning: Large-Scale SES special use in FR/AR districts; NO CREO adopted by 11/29/2024 per plaintiffs | Pletcher et al. v. RWE Solar Development LLC & Otsego County, 46th Circuit Ct (Otsego), Judge Colin Hunter; filed Feb 2025 by atty David Delaney; plaintiffs Gregory & Marcy Beauchesne, Jeffery & Rachel Davis, Charles & Bernadette Pletcher, Ian Murphy. Case no. & current status NOT FOUND publicly. Earlier opposition to DNR land lease (50 House Republicans, Jan 2025). | YES | Pletcher et al. plaintiffs; Fight4Michigan | https://americas.rwe.com/projects-and-locations/rwe-in-michigan/ ; https://www.otsegocountymi.gov/AgendaCenter/ViewFile/Minutes/_02032025-1171 ; https://www.michigannewssource.com/2025/04/exclusive-otsego-county-residents-sue-over-controversial-solar-farm-approval/ ; https://michiganadvance.com/2025/04/14/otsego-county-residents-lodge-challenge-against-michigans-clean-energy-zoning-law-changes/ ; https://otsegocountymi.gov/AgendaCenter/ViewFile/Agenda/_09212026-1378
Poseyville Solar Park | DTE Electric | Ingersoll | Midland | 626+ fenced acres | 129 MWac (DTE/hearing notice); 173 MW per DTE appeal coverage – discrepancy | Denied locally; on appeal | Ingersoll Twp Planning Commission DENIED 6-1 on Apr 21 2026; written decision May 8 2026 | Township solar ordinance (special use); Ordinance #78 (BESS) adopted; no CREO found | DTE Electric Co. v. Ingersoll Township, Midland County (42nd) Circuit Ct No. 2026-428-AA (MCR 7.122 zoning appeal), filed Jun 8 2026 – pending. Recall petitions vs Supv. Kim Heisler + 3 board members (filed Jun 1 2026 by Alicia Marolf) – later denied over filing error per Midland Daily News. | YES | Ingersoll recall organizers | https://ingersolltwpmi.gov/wp-content/uploads/2026/02/fixed-for-Mary-Ellen.pdf ; https://www.ourmidland.com/news/article/ingersoll-township-planning-commission-denies-dte-22217316.php ; https://www.ourmidland.com/news/article/dte-appeals-ingersoll-township-denial-poseyville-22303042.php ; https://www.scribd.com/document/1050337639/DTE-Energy-appeals-Ingersoll-Township-denial ; https://www.themidwesterner.news/2026/06/ingersoll-township-faces-uncertainty-amid-dte-lawsuit-and-halted-effort-to-recall-board-members/ ; https://www.ourmidland.com/news/article/recall-petitions-lee-ingersoll-22387148.php
Northern Waters Solar Park | EDP Renewables North America | Grant | Cheboygan | 810 (project); 1,700 leased | 110 MW | County SUP vacated; PA 233 pre-filing (public mtg Sep 9 2026); MPSC application expected late 2026 (no U-docket yet) | Cheboygan Co. Planning Commission SUP Aug 2025 – VACATED by 53rd Circuit Judge Gauthier ~late Mar 2026 | County zoning; county CREO provision rescinded Jan 2026; 6-month large-solar moratorium adopted Mar 18 2026 (extendable) | Johnson et al. v. Northern Waters Solar Park LLC, EDP Renewables & Cheboygan County, 53rd Cir. Ct (19 plaintiffs; atty David Delaney; filed Oct 2025) – SUP vacated; EDP appeal to COA (docket reported as 380690 – UNVERIFIED) | YES | Johnson et al. plaintiff coalition (19) | https://upnorthlive.com/news/local/judge-vacates-permit-for-810-acre-northern-waters-solar-project-in-cheboygan-county-grant-township-edp-renewables ; https://www.wcmu.org/local-regional-news/2026-09-10/proposed-solar-farm-draws-pushback-at-public-meeting-in-cheboygan-county ; https://www.cheboygannews.com/story/news/local/2026/02/09/cheboygan-countys-grant-township-solar-project-receives-eglefunding/88548606007/ ; https://www.cheboygancounty.net/2026/08/13/northern-waters-solar-llc-notice-of-public-meeting/ ; https://www.michigancapitolconfidential.com/news/19-residents-sue-northern-waters-solar-cheboygan-county-over-1700-acre-solar-project ; https://www.themidwesterner.news/2025/10/cheboygan-county-residents-sue-to-stop-1700-acre-solar-power-plant/
Shipyard Solar | Ranger Power | Grant; Wexford (Wexford Joint PC) | Grand Traverse; Wexford | ~1,800 fenced | Up to 375 MW solar + 375 MW BESS | PA 233 pre-application notices (Aug 2026); no site plan filed | None yet | No CREO confirmed; developer asked localities to confirm none | Grant Twp retained atty Christopher Patterson (Sep 1 2026); organized resident opposition |  |  | https://www.interlochenpublicradio.org/ipr-news/2026-09-04/local-officials-hire-lawyers-respond-to-large-scale-solar-plans-in-northern-michigan ; https://www.9and10news.com/2026/09/01/grant-township-retains-attorney-for-response-to-1800-acre-solar-plans/ ; https://grant-grdtraverse.com/april-8-2026-planning-commission-meeting-agenda/
Acceleration Solar (U-21932) | Ranger Power | Leslie, Onondaga, Vevay | Ingham | 873 | 90 MW | Certificate granted | MPSC, Aug 27 2026 (settlement); CPA PPA w/ Consumers approved | No CREO in ALUs | Townships intervened then settled; Ingham Co. host agreement |  |  | https://www.michigan.gov/mpsc/commission/news-releases/2026/08/27/mpsc-approves-siting-settlement-on-ingham-county-solar-project ; https://www.lansingstatejournal.com/story/news/local/2026/02/16/solar-farm-proposal-ingham-county-leslie-vevay-onondaga-townships/88646190007/
Otisville Solar (U-21956) | EDF | Forest, Thetford | Genesee |  | 125 MW | MPSC under review, complete application | MPSC pending | unverified | Developer amicus in MSC 170249; local intervention unverified |  |  | https://www.michigan.gov/mpsc/regulatory/facility-siting/renewable-energy-and-storage-facility-siting
Washtenaw Solar Energy (U-21962) | Invenergy | Saline | Washtenaw |  | 150 MW | MPSC under review, complete application | MPSC pending | unverified | Saline Twp intervened (testimony Mar 13 2026) |  |  | https://www.michigan.gov/mpsc/regulatory/facility-siting/renewable-energy-and-storage-facility-siting ; https://mi-psc.my.site.com/sfc/servlet.shepherd/version/download/068cs00001oqZdzAAE
Rouget Road Solar (U-22003) | RWE | Palmyra | Lenawee |  | 175 MW | MPSC under review | MPSC pending | unverified | unverified |  |  | https://www.michigan.gov/mpsc/regulatory/facility-siting/renewable-energy-and-storage-facility-siting
Headland Solar (U-22004) | Ranger Power | Cohoctah, Conway | Livingston |  | 220 MW | MPSC under review, complete application | MPSC pending | unverified | Cohoctah & Conway intervened; individual residents (Haas, Parker) petitioned to intervene; both twps are appellants in MSC 170249 |  |  | https://www.michigan.gov/mpsc/regulatory/facility-siting/renewable-energy-and-storage-facility-siting ; https://mi-psc.my.site.com/sfc/servlet.shepherd/version/download/068cs00002BdT4SAAV ; https://mi-psc.my.site.com/sfc/servlet.shepherd/version/download/068cs00001vnh5qAAA
Glacier Meadows Solar (U-22044) | Ørsted Onshore North America | Blissfield, Deerfield | Lenawee |  | 200 MW | MPSC under review, complete application | MPSC pending | unverified (note: a different Deerfield Twp in Lapeer Co. has a CREO) | Blissfield & Deerfield Twps are appellants in MSC 170249 |  |  | https://www.michigan.gov/mpsc/regulatory/facility-siting/renewable-energy-and-storage-facility-siting
Silver Maple Solar (U-22071) | RWE | Jamestown, Zeeland | Ottawa | ~1,900 | 200 MW | MPSC under review | MPSC pending | unverified | Zeeland Charter Twp v. Silver Maple PV LLC et al., Ottawa Co. Cir. Ct 26-08947-CZ (filed Jul 7 2026; Const. art 7 §29), removed to W.D. Mich. 1:26-cv-02280 (Judge Maloney), remand sought; Sen. Runestad opposition (X-only lead). Separate: RWE v. Smallegan family (20th Cir. Ct, Judge Jon Hulsing) – Oct 14 2026 ruling for RWE upholding 563-acre lease & barring Smallegans as MPSC intervenors; appeal expected. MPSC schedule: cross-exam Oct 12-15 2026, PFD Jan 13 2027, final order Apr 3 2027 |  | 'Save Family Farms, Stop Solar Takeover' sign campaign (Zeeland/Jamestown); separately, 20+ adjacent residents are MPSC intervenors in U-22071 | https://www.michigan.gov/mpsc/regulatory/facility-siting/renewable-energy-and-storage-facility-siting ; https://www.pacermonitor.com/public/case/66135057/ZEELAND_CHARTER_TOWNSHIP_v_SILVER_MAPLE_PV,_LLC_et_al ; https://www.hollandsentinel.com/story/government/local/zeeland-township/2026/07/08/zeeland-township-files-lawsuit-to-strike-down-public-act-233/90837130007/ ; https://www.ottawanewsnetwork.org/developers-push-zeeland-townships-battle-over-state-solar-law-to-federal-court/ ; https://x.com/Grimillionaire/status/2108321857174921462 ; https://whtc.com/2026/10/15/judge-rules-in-favor-of-rwe-in-silver-maple-solar-farm-lawsuit/ ; https://www.fox17online.com/news/local-news/holland-zeeland/zeeland-township-neighbors-fight-to-stay-in-solar-farm-approval-process-as-legal-battle-takes-shape
Birch Valley Solar (U-22072) | Ranger Power | Arbela | Tuscola |  | 162 MW | MPSC under review, complete application | MPSC pending | unverified | Resident Donald Wellington petitioned to intervene (opposed by developer); Tuscola Co. appellant in MSC 170249 |  |  | https://www.michigan.gov/mpsc/regulatory/facility-siting/renewable-energy-and-storage-facility-siting ; https://mi-psc.my.site.com/sfc/servlet.shepherd/version/download/068cs0000260EwBAAU
Walker Road Solar (U-22130) | RWE | Bingham | Clinton |  | 150 MW | MPSC under review | MPSC pending | unverified | Bingham Twp & Clinton Co. appellants in MSC 170249 |  |  | https://www.michigan.gov/mpsc/regulatory/facility-siting/renewable-energy-and-storage-facility-siting
Lakeside Solar (U-22143) | Geronimo Power | White River | Muskegon |  | 150 MW + 150MW/600MWh BESS | MPSC incomplete application (filed Jul 6 2026) | Twp 'approved' SLU w/ 52 conditions Jan 8 2026 – developer calls it functional denial | Township overlay district ordinance | White River Twp appellant in MSC 170249 |  |  | https://www.michigan.gov/mpsc/regulatory/facility-siting/renewable-energy-and-storage-facility-siting ; https://mi-psc.my.site.com/sfc/servlet.shepherd/version/download/068cs00002Cnhs3AAB
Fiddlehead Solar (U-22041) | Hecate Energy (Springport Solar LLC) | Brookfield, Hamlin, Springport | Eaton; Jackson |  | 225 MW | MPSC incomplete application | MPSC pending | unverified | unverified |  |  | https://www.michigan.gov/mpsc/regulatory/facility-siting/renewable-energy-and-storage-facility-siting
Sylvan Solar (U-22242) | AES | Garfield, Sheridan Charter | Newaygo |  | 220 MW | MPSC under review | MPSC pending | unverified | Garfield Twp appellant in MSC 170249 (may be a different Garfield – unverified) |  |  | https://www.michigan.gov/mpsc/regulatory/facility-siting/renewable-energy-and-storage-facility-siting
Heartwood Solar II | Ranger Power | Fayette | Hillsdale | ~1,350–1,400 leased; ~1,000 fenced | 140 MW | Denied locally; developer suing | Fayette Twp PC DENIED 4-0, Jun 1 2026 | CREO adopted Apr 2026 | Heartwood Solar II LLC v. Fayette Twp, Hillsdale Co. Cir. Ct (filed Jul 2026; no. unverified); opposition led by Steve Oleszkowicz; Hillsdale College opposed |  | No Solar Fayette https://nosolarfayette.com/ | https://www.mlive.com/news/jackson/2026/08/a-michigan-township-that-said-no-to-a-2nd-big-solar-project-is-now-in-a-legal-fight.html ; https://wtvbam.com/2026/06/02/945299/ ; https://www.mlive.com/news/jackson/2026/03/michigan-township-seeking-control-over-project-that-could-add-1000-acres-of-solar-panels.html
Gustin Solar (fka Sapling Solar) | Consumers Energy (acq. from Ranger Power Sep 2025) | Gustin, Harrisville | Alcona | 3,985.6 total; 2,684.2 solar | 335 MW | Gustin SUP denied Aug 6 2026; Harrisville vote Oct 2026 (result unverified) | Gustin Twp approved earlier version 2024; denied expansion 2026 | unverified | Organized opposition; Rep. Cam Cavitt opposed; no suit found |  |  | https://www.thealpenanews.com/news/local-news/2026/08/utility-scale-solar-project-in-alcona-county-in-limbo/
Strasburg Solar Park | DTE Electric | Raisinville | Monroe | ~500–545 | 100 MW | Re-application; PC recommended approval 5-0 Sep 21 2026; board vote pending | Twp Board denied Jun 2 2026; re-review | Township solar ordinance §3.31 | Large resident opposition at hearings (~160 attendees); no suit found |  |  | https://www.monroenews.com/story/news/local/2026/05/22/500-acre-solar-park-field-farm-raisinville-township-dte-energy-strasburg-solar-park/90196500007/ ; https://www.raisinville.org/mt-content/uploads/2026/09/09-september-21-pc-solar-meeting.docx.pdf
Portside Solar | Portside Solar LLC (PPA w/ Consumers approved by MPSC); DTE co-plaintiff vs county | unverified | St. Clair |  | unverified | unverified | MPSC PPA approval | County health-code solar regs struck Feb 2 2026 (Judge Michael West); county appealing | DTE & Portside Solar v. St. Clair County, St. Clair Cir. Ct – summary judgment for developers; county appeal to COA (no. unverified) |  |  | https://www.thetimesherald.com/story/news/local/2026/02/03/st-clair-county-michigan-solar-regulations-overturned-what-to-know/88492384007/ ; https://www.thetimesherald.com/story/news/local/2026/02/23/st-clair-county-appeals-solar-power-ruling/88827681007/ ; https://adms.apps.lara.state.mi.us/Mpsc/ViewCommissionOrderDocument/27472
Watertown Solar | unverified (Watertown Solar LLC; PPA w/ Consumers) | unverified | unverified |  | 150 MW | PPA approved | MPSC U-21090, Feb 19 2026 (PPA) | unverified | Watertown Twp is appellant in MSC 170249 (link unverified) |  |  | https://adms.apps.lara.state.mi.us/Mpsc/ViewCommissionOrderDocument/27587
Mendon Solar | Consumers Energy (self-developed) | unverified (likely Mendon Twp) | unverified (likely St. Joseph) |  | 150 MW | Selected in 2024 RFP | unverified | unverified | unverified |  |  | https://adms.apps.lara.state.mi.us/Mpsc/ViewCommissionOrderDocument/27587
Liberty Farms Solar | unverified | Richland | Kalamazoo | 2,268 | 220 MW | Township PC review (Mar 2026) | pending | unverified | unverified |  |  | https://cms2.revize.com/revize/richlandtwpkc/PC%20Packet%20B%2003-25-26.pdf?t=202603191633330
Blazing Star Solar | unverified | Way | Gratiot |  | 125 MW | PC conditional approval 4-3 (Jun 10 2026) | Way Twp PC Jun 10 2026 | Township solar ordinance (unverified) | unverified |  |  | https://waytwp.org/wp-content/uploads/2026/07/6-10-26.pdf
Flint Twp GM landfill solar | AC Power | Flint | Genesee |  | unverified | Site plan approved Feb 2026 | Flint Twp | unverified | none found |  |  | https://www.mlive.com/news/flint/2026/02/solar-energy-site-plan-approved-at-former-gm-landfill-in-flint-township.html

## Priority Projects
Project | Item | Detail | Date | Source
45th Parallel (Otsego) | Local approval | Otsego Co. PC SUP/site plan PZSU24-017, Hayes Twp Secs 3,4,9,10,16,17,19,20,21,28; FR & AR districts | 2025-02-03 | https://www.otsegocountymi.gov/AgendaCenter/ViewFile/Minutes/_02032025-1171
45th Parallel (Otsego) | Lawsuit | Pletcher et al. v. RWE Solar Development & Otsego County, Otsego Co. Cir. Ct, Judge Colin Hunter; claims: county lacked authority w/o CREO, PA 233 vague/unlawful delegation, nuisance; seeks injunction. Filed Feb 2025 by David Delaney; plaintiffs Beauchesne, Davis, Pletcher, Ian Murphy. Case no./status not public online – pull from 46th Circuit clerk / plaintiffs' file | 2025-04 | https://www.michigannewssource.com/2025/04/exclusive-otsego-county-residents-sue-over-controversial-solar-farm-approval/
45th Parallel (Otsego) | MPSC | U-21816: Consumers BTA application Oct 15 2025 (ex parte, PA 235 §28(6)); approved Nov 6 2025; BTA signed Sep 30 2025; 138 kV METC; COD 12/31/2027; ~$436M capital cost per State Affairs | 2025-11-06 | https://mi-psc.my.site.com/sfc/servlet.shepherd/version/download/068cs00001NipAjAAJ
45th Parallel (Otsego) | County PC | 'RWE Solar Project Update' agenda items; Sept PC discussed Trina Solar bifacial panels | 2026-05-18; 2026-09-21 | https://otsegocountymi.gov/AgendaCenter/ViewFile/Agenda/_09212026-1378
45th Parallel (Otsego) | People | Hayes Twp Supv. Mary Sanders; PC Chair Maxwell; plaintiffs incl. Pletcher family |  | https://www.otsegocountymi.gov/AgendaCenter/ViewFile/Minutes/_02032025-1171
45th Parallel (Otsego) | MISO | Likely J1603 (200 MW, Otsego, Vantyle 138 kV POI, status Done) – inferred. ALSO J3134: 150 MW solar, Otsego, Wolverine Power Supply Co-op, Gaylord Interconnection, queued 2022-09-15, Active – a SECOND Otsego solar request, developer unidentified (possible additional RWE or other project) – investigate | 2026-10-20 | https://www.misoenergy.org/api/giqueue/getprojects
Poseyville (Ingersoll/Midland) | MISO | Likely J2877 (129.0 MW, Midland, Murphy–Tittabawassee 345 kV, Active) – inferred from MW match, UNVERIFIED | 2026-10-20 | https://www.misoenergy.org/api/giqueue/getprojects
Poseyville (Ingersoll/Midland) | Public hearing | PC public hearing on DTE SUP, 129 MWac, 626+ fenced acres, Secs 10,15,21,22,27; parcels Garrett Family Farm/Garrett Land Co., Radosa, Thurlow, Wylie, Terwillegar Sons | 2026-03-16 | https://ingersolltwpmi.gov/wp-content/uploads/2026/02/fixed-for-Mary-Ellen.pdf
Poseyville (Ingersoll/Midland) | Denial | PC 6-1 denial (parcel contiguity, property-line noise); Chair Suzette Loeffler; written decision May 8 | 2026-04-21 | https://www.ourmidland.com/news/article/ingersoll-township-planning-commission-denies-dte-22217316.php
Poseyville (Ingersoll/Midland) | Lawsuit | DTE Electric Co. v. Ingersoll Twp, 42nd Cir. Ct (Midland) No. 2026-428-AA, appeal of right MCR 7.122; DTE counsel Miller Johnson (Emily Palacios, David Szymanski); twp counsel Andrew C. Thompson (Poznak Dyer Kanar Schefsky Thompson). Pending; no hearing date found | 2026-06-08 | https://www.scribd.com/document/1050337639/DTE-Energy-appeals-Ingersoll-Township-denial
Poseyville (Ingersoll/Midland) | Ordinance | Ordinance #78 (BESS, special use) – basis of recall | 2026 | https://www.themidwesterner.news/2026/06/ingersoll-township-faces-uncertainty-amid-dte-lawsuit-and-halted-effort-to-recall-board-members/
Poseyville (Ingersoll/Midland) | Recall | Petitions by Alicia Marolf vs Supv. Kim Heisler, Trustee Ron Garrett, Treas. Jim Terwillegar + 1; clarity approved 6/12; officials appealed 6/18; later denied over filing error | 2026-06 | https://www.ourmidland.com/news/article/recall-petitions-lee-ingersoll-22387148.php
Poseyville (Ingersoll/Midland) | MPSC | No PA 233 MPSC docket found for Poseyville (DTE is a utility; PA 233 path also open to electric providers – unverified whether DTE intends to file)
Midland County generally | Ordinances | Siting Radar lists Ingersoll data-center ordinance and a 'solar moratorium' agenda item (Jun 9 2026, jurisdiction unclear) – UNVERIFIED lead | 2026 | https://sitingradar.com/states/mi/counties/midland-county
Northern Waters (Grant Twp, Cheboygan) | Project | EDP Renewables NA; 110 MW; 810 fenced / ~1,700 leased acres; bounded by Trudeau & Chamberlain Rds, Twin Lakes & N. Black River Rds; EGLE Renewables Ready $275k to Grant Twp (+$275k county eligible); MISO queue likely match J1929 (110.0 MW, Cheboygan, METC, queued 2021-08-24, Active) – inferred from MW/county, UNVERIFIED; also J3777 (91.8 MW, Cheboygan, Mill Creek 138 kV) is another Cheboygan solar request – developer unknown |  | https://www.cheboygannews.com/story/news/local/2026/02/09/cheboygan-countys-grant-township-solar-project-receives-eglefunding/88548606007/
Northern Waters (Grant Twp, Cheboygan) | County approval | Cheboygan Co. Planning Commission granted SUP | 2025-08 | https://www.themidwesterner.news/2025/10/cheboygan-county-residents-sue-to-stop-1700-acre-solar-power-plant/
Northern Waters (Grant Twp, Cheboygan) | Lawsuit | Johnson et al. v. Northern Waters Solar Park LLC, EDP Renewables & Cheboygan County, 53rd Circuit Ct; 19 plaintiffs (Robert & Betty Johnson, Joseph & Sharon Long, Glen & Debra Buehner, Clark & Dawn Compton, William & Doris Wisnieski, Richard & Marla Peltier, Eric Boyd, Eric & Sandra Delamielleure, Anthony & Antoinette Zalewski); atty David Delaney; also challenges PA 233 (equal protection). Circuit case no. UNVERIFIED | 2025-10 | https://www.michigancapitolconfidential.com/news/19-residents-sue-northern-waters-solar-cheboygan-county-over-1700-acre-solar-project
Northern Waters (Grant Twp, Cheboygan) | Court order | Judge Gauthier (53rd Cir.) reversed & VACATED SUP from bench: PC made no findings under Zoning Ord. §§18 & 20 (special land use standards) – findings required even with CREO/use-by-right language. Earlier January 2026 ruling also referenced (county then rescinded CREO language). Exact order date UNVERIFIED (reported 'last week' on Apr 2 2026) | ~2026-03-26 | https://upnorthlive.com/news/local/judge-vacates-permit-for-810-acre-northern-waters-solar-project-in-cheboygan-county-grant-township-edp-renewables
Northern Waters (Grant Twp, Cheboygan) | Appeal | EDP appealing to Michigan Court of Appeals; docket reported as COA 380690 (Johnson v Northern Waters Solar Park LLC) by search summary only – UNVERIFIED; courts.michigan.gov internal case ID 112236 surfaced but page did not render | 2026 | https://www.courts.michigan.gov/c/courts/coa/case/112236 ; https://www.wcmu.org/local-regional-news/2026-09-10/proposed-solar-farm-draws-pushback-at-public-meeting-in-cheboygan-county
Northern Waters (Grant Twp, Cheboygan) | Ordinance | County CREO provision rescinded day after Jan 2026 ruling; large-scale solar moratorium official Mar 18 2026 for 6 months (extendable – extension status UNVERIFIED) | 2026-03-18 | https://upnorthlive.com/news/local/judge-vacates-permit-for-810-acre-northern-waters-solar-project-in-cheboygan-county-grant-township-edp-renewables
Northern Waters (Grant Twp, Cheboygan) | PA 233 / MPSC | Developer notice to county Aug 2026; PA 233 public meeting Sep 9 2026 at Chateau at Black Mountain (250+ attendees, ~40 comments); MPSC application expected late 2026; construction 2028, COD 2029. No U-docket yet | 2026-09-09 | https://www.cheboygancounty.net/2026/08/13/northern-waters-solar-llc-notice-of-public-meeting/ ; https://now.solar/2026/09/21/northern-waters-solar-project-moves-closer-to-state-review-cheboygannews-com/
Northern Waters (Grant Twp, Cheboygan) | People | EDPR spokesperson Amy Varghese; EDP VP Thomas LoTurco; opponents Deb Buehner, Sherry Long, Joseph Long, Jim Coleman |  | https://www.wcmu.org/local-regional-news/2026-09-10/proposed-solar-farm-draws-pushback-at-public-meeting-in-cheboygan-county
Shipyard (Grant Twp, Grand Traverse) – note | Note | Different Grant Twp; kept as normal row only |  | https://www.interlochenpublicradio.org/ipr-news/2026-09-04/local-officials-hire-lawyers-respond-to-large-scale-solar-plans-in-northern-michigan
Northern Waters (Grant Twp, Cheboygan) | Summary | Landowner suit vacated county SUP (Apr 2026); EDP appealing; PA 233 public meeting Sep 9 2026 (250+ attendees); MPSC filing expected late 2026. Opponents: Deb Buehner, Robert & Betty Johnson, Sherry Long, Jim Coleman | 2026 | https://now.solar/2026/09/21/northern-waters-solar-project-moves-closer-to-state-review-cheboygannews-com/
Shipyard (Grand Traverse) [non-priority] | PA 233 notice | Ranger notice mid-Aug 2026; 30-day response; Twp hired Christopher Patterson 9/1/2026; Trustee Doug Moyer; resident Barb Wilson PA 233 handout | 2026-09-01 | https://upnorthlive.com/news/local/grant-township-solar-energy-storage-project-hires-attorney-as-375-megawatt-moves-forward-ranger-power-shipyard-grand-traverse-northern-michigan-upnorthlive
Statewide | PA 233 rules case | In re Implementing Provisions of PA 233 (MPSC U-21547): COA 373259 upheld most rules, struck CREO timeline & narrow ALU def. (5/7/2026); MSC 170249 leave pending; atty Michael Homier for 79 locals | 2026 | https://www.mlive.com/environment/2026/06/townships-ask-michigan-supreme-court-to-hear-permitting-fight-for-wind-solar-farms.html

## CREO & PA233 Litigants
Jurisdiction | County | Category | Detail | Source
Bertrand Charter Twp | Berrien | CREO adopted | Ord. 241114A, adopted 11/14/2024 | https://www.bertrandtwpmi.gov/api/blob/viewBlob?i=Qs3xIcdzHdsR9PoXxLQUdkymgkN5Pay0pWLXwhqgpribTlTFMraYh4Xvc8GQQbGp&rf=t
Elbridge Twp | Oceana | CREO adopted | Ord. 14, adopted 2/11/2025 | https://elbridgetownship.org/wp-content/uploads/2025/03/CREO-Ordinance-02112025.pdf
Charter Twp of Oakland | Oakland | CREO adopted | Ord. 113, adopted 2/11/2025 | https://ecode360.com/OA3183/laws/LF2462572.pdf
Deerfield Twp | Lapeer (Linden address) | CREO adopted | Ord. 112-37 | https://deerfieldtwp.org/documents/ordinance-no-112-37-creo/
Fayette Twp | Hillsdale | CREO adopted | Adopted Apr 1 2026 | https://hillsdale.community.diligentoneplatform.com/document/40ec5cab-d7b2-4b33-9899-e1cdb9075e09/?modified=2026-04-28T18%3A38%3A12.367
Cheboygan County | Cheboygan | CREO rescinded; moratorium | CREO language removed Jan 2026; large-solar moratorium Mar 18 2026 (6 mo.) | https://upnorthlive.com/news/local/judge-vacates-permit-for-810-acre-northern-waters-solar-project-in-cheboygan-county-grant-township-edp-renewables
Otsego County | Otsego | Solar ordinance (2021); no CREO | Per Pletcher complaint coverage | https://www.petoskeynews.com/story/news/local/2025/04/17/lawsuit-challenges-hayes-township-solar-projects-legality/83115055007/
Minden Twp | Sanilac | Solar ordinance (referendum failed) | Adopted 3/3/2025; referendum petition invalidated, COA affirmed Jun 5 2026 | https://sanilaccountynews.com/articles/petitioners-lose-appeal-to-put-minden-twp-solar-on-ballot/
Zeeland Charter Twp | Ottawa | Suing over PA 233 | 26-08947-CZ / W.D. Mich 1:26-cv-02280 | https://www.pacermonitor.com/public/case/66135057/ZEELAND_CHARTER_TOWNSHIP_v_SILVER_MAPLE_PV,_LLC_et_al
Almer Charter Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Argentine Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Augusta Charter Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Beaver Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Bengal Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Bingham Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Blissfield Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Bridgehampton Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Brockway Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Cascade Charter Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Cato Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Clinton County | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Cohoctah Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Columbia Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Columbus Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Conway Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Cooper Charter Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Dallas Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Deerfield Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Denmark Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Douglass Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Duplain Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Eagle Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Easton Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Ellington Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Elmwood Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Escanaba Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Frankenlust Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Fremont Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Garden Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Garfield Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Genoa Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Handy Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Ida Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Ingham Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Ionia County | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Iosco Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Isabella Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Joyfield Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Juniata Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Kawkawlin Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Keene Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Kimball Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Lake Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Leroy Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Marion Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Milan Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Monitor Charter Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Montague Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Montcalm Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Moore Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
North Branch Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Ogden Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Orleans Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Riga Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Sanilac County | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Schoolcraft County | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Seville Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Shiawassee County | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Sidney Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Speaker Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Stockbridge Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Summerfield Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Tuscola County | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Tyrone Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Venice Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Wales Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Waterloo Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Watertown Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
White Oak Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
White River Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Williams Charter Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Worth Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
York Charter Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf
Paris Township | (not stated in order) | Appellant – PA 233 rules challenge | COA 373259 (pub. op. 5/7/2026, split) -> MSC 170249 (lv app filed 6/18/2026; amici accepted 9/9/2026) | https://insidemichigan.org/solar/records/files/msc-170249-order-2026-09-09.pdf ; https://www.courts.michigan.gov/siteassets/case-documents/uploads/OPINIONS/FINAL/COA/20260507_C373259_140_373259.opn.pdf

## Facebook Opposition Groups
Group name | URL | Linked project / township / county | Public/private | Approx. members | Platform | Notes
No Solar Fayette (Empowering Fayette) | https://nosolarfayette.com/ | Heartwood Solar II / Fayette Twp / Hillsdale | Public website | n/a | Website (not Facebook) | info@nosolarfayette.com; leader Steve Oleszkowicz. FB page UNVERIFIED
'Save Family Farms, Stop Solar Takeover' sign campaign | https://www.woodtv.com/news/ottawa-county/zeeland-township-letter-appeals-to-president-to-stop-solar-project/ | Silver Maple / Zeeland & Jamestown / Ottawa | n/a | n/a | Yard-sign campaign | FB group UNVERIFIED
Northern Waters plaintiffs (Johnson/Long/Buehner et al.) | https://www.michigancapitolconfidential.com/news/19-residents-sue-northern-waters-solar-cheboygan-county-over-1700-acre-solar-project | Northern Waters / Grant Twp / Cheboygan | n/a | 19 plaintiffs | Litigant coalition | FB group UNVERIFIED
Ingersoll recall organizers (Alicia Marolf) | https://www.themidwesterner.news/2026/06/ingersoll-township-faces-uncertainty-amid-dte-lawsuit-and-halted-effort-to-recall-board-members/ | Poseyville / Ingersoll / Midland | n/a | n/a | Informal | FB group UNVERIFIED
Fight4Michigan / IRON Foundation | https://fight4michigan.org/why-we-fight | 45th Parallel + statewide | Public website | n/a | Website | User's own foundation site (describes Pletcher suit)

## MISO Queue MI Solar
MISO # | Queue date | Status | Post-GIA status | County | TO | POI | Summer MW | Fuel | Study cycle/phase | Requested in-service | Source
J3451 | 2024-04-05 | Active |  | Alcona | METC | IOSCO - SPRUCE ROAD 138.0kV | 120 | Solar | DPP-2023 Phase 2 | 2027-04-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J2611 | 2022-09-14 | Active | Not Started | Alcona | METC | IOSCO - SPRUCE ROAD 138.0kV | 215 | Solar | DPP-2022 Phase 2 | 2028-09-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J3539 | 2024-03-28 | Active |  | Alcona | METC | ALPENA - SPRUCE ROAD 138.0kV | 116.9 | Solar | DPP-2023 Phase 2 | 2027-04-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J3644 | 2024-04-18 | Active |  | Bay | METC | Other_ | 150 | Solar | DPP-2023 Phase 2 | 2028-11-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J2874 | 2022-08-31 | Active | Not Started | Bay | METC | HAMPTON | 85 | Solar | DPP-2022 Phase 2 | 2025-11-15 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J1550 | 2020-06-22 | Done | In Service | Branch | METC | BARTON LAKE - BATAVIA 138.0kV | 200 | Solar | DPP-2020 GIA | 2024-07-04 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J1916 | 2023-10-19 | Active | Not Started | Branch | Michigan Electric Transmission Company LLC | NEWTON | 100 | Solar | DPP-2021 Phase 3 | 2023-11-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J1320 | 2019-04-29 | Done | Not Started | Branch County | METC | Coldwater - Batavia 138kV Line | 150 | Solar | DPP-2019 GIA | 2019-04-20 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J1401 | 2019-04-29 | Done | In Service | Branch County | METC | Batavia - Wagner 138kV Line | 150 | Solar | DPP-2019 GIA | 2023-11-17 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J2098 | 2021-08-22 | Active | Not Started | Calhoun | METC | BATTLE CREEK - ONEIDA 345.0kV | 309 | Solar | DPP-2021 Phase 3 | 2025-03-31 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J2921 | 2022-09-15 | Active | Not Started | Calhoun |  | Other_ | 250 | Solar | DPP-2022 Phase 2 | 2026-08-31 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J3050 | 2025-07-29 | Active | Not Started | Calhoun | METC | MAJESTIC - ONEIDA 345.0kV | 255 | Solar | DPP-2022 Phase 2 | 2027-04-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J1248 | 2019-04-29 | Done | Not Started | Calhoun County | METC | Marshall - Black Stone 138 kV line | 100 | Solar | DPP-2019 GIA | 2021-08-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J1430 | 2019-04-29 | Done | Not Started | Calhoun County | METC | Verona - Foundary 138kV Line | 100 | Solar | DPP-2019 GIA | 2022-08-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J806 | 2017-06-16 | Done | In Service | Calhoun County | METC | Rice Creek - Vrooman 138kV Line Tap | 149 | Solar | DPP-2017-AUG GIA | 2019-09-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J758 | 2016-11-14 | Done | In Service | Calhoun County | METC | Verona-Foundry 138kV | 200 | Solar | DPP-2017-FEB GIA | 2018-10-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J857 | 2017-06-16 | Done | Under Construction | Calhoun County | METC | Verona - Foundry 138 kV Line Tap | 124.95 | Solar | DPP-2017-AUG GIA | 2019-09-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J4102 | 2025-10-10 | Active |  | Cass | METC | WEEDS LAKE - HIPLE 345.0kV | 539 | Solar | DPP-2026 | 2029-08-31 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J3777 | 2024-04-12 | Active |  | Cheboygan | METC | MC GULPIN - RIGGSVILLE (MILL CREEK) 138.0kV | 91.8 | Solar | DPP-2023 Phase 2 | 2028-04-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J1929 | 2021-08-24 | Active | Not Started | Cheboygan | METC | Other_ | 110 | Solar | DPP-2021 Phase 3 | 2025-10-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J1553 | 2021-12-03 | Done | Not Started | Clinton | METC | BINGHAM | 150 | Solar | DPP-2020 GIA | 2023-09-15 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J2678 | 2022-09-14 | Active | Not Started | Delta | AMERICAN TRANSMISSION COMPANY | Chandler 138 kV | 150 | Solar | DPP-2022 Phase 2 | 2025-11-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J1183 | 2018-03-12 | Done | In Service | Delta County | American Transmission Co. LLC | Heritage Garden substation | 1.35 | Solar | DPP-2018-APR GIA | 2019-01-31 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J1814 | 2020-06-24 | Done | Not Started | Dickinson | AMERICAN TRANSMISSION COMPANY | Nordic | 22.5 | Solar | DPP-2020 GIA | 2023-09-15 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J2316 | 2021-09-16 | Active | Not Started | Dickinson | AMERICAN TRANSMISSION COMPANY | Nordic 138kV Substation | 77.5 | Solar | DPP-2021 Phase 3 | 2023-09-15 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J4085 | 2025-10-07 | Active |  | Dickinson | AMERICAN TRANSMISSION COMPANY | Nordic | 42 | Solar | DPP-2025 Phase 1 | 2027-10-15 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J4169 | 2025-10-06 | Active |  | Dickinson | AMERICAN TRANSMISSION COMPANY | Nordic | 5.99 | Solar | DPP-2025 Phase 1 | 2025-09-15 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J1172 | 2018-03-12 | Done | Under Construction | Genesee County | METC | Dort - Garfield 138 kV Line Tap | 50 | Solar | DPP-2018-APR GIA | 2021-07-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J1203 | 2019-04-25 | Done | Under Construction | Genesee County | METC | Thetford 345kV Substation | 125 | Solar | DPP-2019 GIA | 2022-06-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J3792 | 2024-04-18 | Active |  | Gratiot | METC | ALMA - VESTABURG 138.0kV | 125 | Solar | DPP-2023 Phase 2 | 2028-04-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J3722 | 2024-03-27 | Active |  | Hillsdale | METC | COLDWATER - MOORE ROAD 138.0kV | 150 | Solar | DPP-2023 Phase 2 | 2028-09-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J1658 | 2025-05-19 | Done | Not Started | Hillsdale | METC | COLDWATER - MOORE ROAD 138.0kV | 180 | Solar | DPP-2020 GIA | 2023-09-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J2812 | 2022-09-14 | Active | Not Started | Hillsdale | METC | MOORE ROAD | 140 | Solar | DPP-2022 Phase 2 | 2026-09-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J3419 | 2024-03-18 | Active |  | Huron | ITC | SEASIDE | 150 | Solar | DPP-2023 Phase 2 | 2028-09-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J2676 | 2022-09-14 | Active | Not Started | Huron | ITC | RAPSON - STEIN 345.0kV | 200 | Solar | DPP-2022 Phase 2 | 2025-11-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J3838 | 2024-04-18 | Active |  | Ingham | METC | DELHI - TOMPKINS 138.0kV | 225 | Solar | DPP-2025 Phase 1 | 2028-11-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J1399 | 2019-04-29 | Done | Not Started | Ingham County | METC | Delhi - Churchill - Tompkins 138kV Line | 90 | Solar | DPP-2019 GIA | 2021-12-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J3545 | 2024-04-15 | Active |  | Ionia | METC | BINGHAM - MARQUETTE 138.0kV | 200 | Solar | DPP-2023 Phase 2 | 2028-09-15 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J1255 | 2019-04-29 | Done | Under Construction | Ionia County | METC | Marquette - Vergennes 138 kV Line Tap | 200 | Solar | DPP-2019 GIA | 2022-10-30 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J1210 | 2019-04-27 | Done | Not Started | Iosco County | METC | Whittemore - Twining 138kV Line | 50 | Solar | DPP-2019 GIA | 2023-10-31 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J1310 | 2019-04-29 | Done | Under Construction | Jackson County | METC | Blackstone - Marshall 138 kV Line | 125 | Solar | DPP-2019 GIA | 2022-06-30 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J1472 | 2019-04-29 | Done | Not Started | Jackson County | METC | Leoni - Parr Raod 138kV line | 100 | Solar | DPP-2019 GIA | 2022-08-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J2814 | 2022-09-07 | Active | Not Started | Kalamazoo | METC | ARGENTA - MORROW 138.0kV | 220 | Solar | DPP-2022 Phase 2 | 2026-02-15 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J3828 | 2024-04-18 | Active |  | Lapeer | ITC | Other_ | 100 | Solar | DPP-2025 Phase 1 | 2028-11-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J1571 | 2021-12-03 | Done | Not Started | Lenawee | METC | MOROCCO | 200 | Solar | DPP-2020 GIA | 2023-09-15 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J4061 | 2025-08-07 | Active |  | Lenawee | ITC | KNOWLES - MOORE ROAD 138.0kV | 150 | Solar | DPP-2026 | 2028-11-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J875 | 2017-06-16 | Done | Under Construction | Lenawee County | METC | Par - Raisin Road 138kV Line | 150 | Solar | DPP-2017-AUG GIA | 2020-09-10 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J996 | 2018-03-12 | Done | Under Construction | Lenawee County | METC | Beecher - Moraco 138kV Line | 80 | Solar | DPP-2018-APR GIA | 2021-09-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J1226 | 2019-04-27 | Done | Under Construction | Lenawee County | METC | Morocco 345 kV Substation | 200 | Solar | DPP-2019 GIA | 2023-09-29 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J2485 | 2022-09-14 | Active | Not Started | Livingston | ITC | BLACKFOOT - MADRID 345.0kV | 180 | Solar | DPP-2022 Phase 2 | 2025-11-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J2679 | 2022-09-14 | Active | Not Started | Livingston | ITC | COLFAX to Madrid 120 kV | 100 | Solar | DPP-2022 Phase 2 | 2027-04-15 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J3827 | 2024-04-18 | Active |  | Mackinac | AMERICAN TRANSMISSION COMPANY | Indian Lake - Hiawatha 138.0kV | 160 | Solar | DPP-2025 Phase 1 | 2028-11-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J1750 | 2022-04-06 | Done | Under Construction | Marquette | AMERICAN TRANSMISSION COMPANY | Other_ | 149.7 | Solar | DPP-2020 GIA | 2023-08-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J2029 | 2021-11-30 | Active | Not Started | Marquette | AMERICAN TRANSMISSION COMPANY | Perch Lake | 62.5 | Solar | DPP-2021 Phase 3 | 2024-09-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J1251 | 2019-04-29 | Done | Under Construction | Marquette County | American Transmission Co. LLC | Arnold - Perkins 138 kV Line Tap | 100 | Solar | DPP-2019 GIA | 2022-10-30 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J2877 | 2022-09-14 | Active | Not Started | Midland | METC | MURPHY - TITTABAWASSEE 345.0kV | 129 | Solar | DPP-2022 Phase 2 | 2025-11-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J2486 | 2022-09-14 | Active | Not Started | Monroe | ITC | LALLENDORF - MONROE 345.0kV | 85 | Solar | DPP-2022 Phase 2 | 2025-11-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J3803 | 2024-04-18 | Active |  | Monroe | ITC | LEMOYNE - MAJESTIC 345.0kV | 200 | Solar | DPP-2023 Phase 2 | 2028-04-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J1379 | 2019-04-29 | Done | Not Started | Montcalm County | METC | Eureka - Vestaburg 138 kV Line Tap | 200 | Solar | DPP-2019 GIA | 2023-10-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J3682 | 2024-04-18 | Active |  | Muskegon | METC | FOUR MILE - WHITE ROAD 138.0kV | 150 | Solar | DPP-2023 Phase 2 | 2028-04-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J1587 | 2020-06-22 | Done | Not Started | Muskegon | ITC | Du Pont to Cobb 138 KV (J1375 POI) | 100 | Solar | DPP-2020 GIA | 2023-09-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J1614 | 2020-06-11 | Done | Not Started | Muskegon | METC | White Road - Four Mile 138kV line | 250 | Solar | DPP-2020 GIA | 2024-02-15 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J1375 | 2019-04-29 | Done | Under Construction | Muskegon County | METC | Du Pont - Cobb -White Lake 138kv | 100 | Solar | DPP-2019 GIA | 2023-09-29 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J2001 | 2021-08-16 | Active | Not Started | Newaygo | METC | KENOWA - LUDINGTON 345.0kV | 220 | Solar | DPP-2021 Phase 3 | 2025-05-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J3065 | 2022-09-15 | Active | Not Started | Oceana | METC | DONALDSON CREEK | 20 | Solar | DPP-2022 Phase 2 | 2025-03-30 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J1071 | 2018-03-12 | Done | Under Construction | Oceana County | METC | Donaldson 138 kV Substation | 100 | Solar | DPP-2018-APR GIA | 2021-01-20 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J3274 | 2024-04-15 | Active |  | Ogemaw | METC | GALLAGHER - TWINING 138.0kV | 290 | Solar | DPP-2023 Phase 2 | 2028-11-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J3761 | 2024-04-05 | Active |  | Ogemaw | METC | GALLAGHER - TWINING 138.0kV | 145.8 | Solar | DPP-2023 Phase 2 | 2027-11-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J3066 | 2022-09-15 | Active | Not Started | Osceola | WOLVERINE POWER SUPPLY COOPERATIVE | Hersey Interconnection | 50 | Solar | DPP-2022 Phase 2 | 2026-06-30 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J1603 | 2021-12-03 | Done | Not Started | Otsego | METC | Vantyle 138kV | 200 | Solar | DPP-2020 GIA | 2023-09-15 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J3134 | 2022-09-15 | Active | Not Started | Otsego | WOLVERINE POWER SUPPLY COOPERATIVE | Gaylord Interconnection | 150 | Solar | DPP-2022 Phase 2 | 2025-06-30 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J1663 | 2021-12-03 | Done | Under Construction | Ottawa | METC | ARGENTA - TALLMADGE 345.0kV | 200 | Solar | DPP-2020 GIA | 2023-09-15 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J1914 | 2023-10-05 | Active | Not Started | Presque Isle | METC | PORT CALCITE - ROCKPORT 138.0kV | 150 | Solar | DPP-2021 Phase 3 | 2023-11-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J3843 | 2024-11-21 | Active |  | Saginaw | METC | GOSS - SLATE 345.0kV | 300 | Solar | DPP-2025 Phase 1 | 2027-11-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J3835 | 2024-07-18 | Active |  | Saginaw | ITC | Other_ | 130 | Solar | DPP-2025 Phase 1 | 2028-11-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J1939 | 2023-10-18 | Active | Not Started | Saginaw | METC | CORNELL - LAYTON 138.0kV | 125 | Solar | DPP-2021 Phase 3 | 2023-11-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J2061 | 2021-08-12 | Active | Not Started | Saginaw | METC | MURPHY | 200 | Solar | DPP-2021 Phase 3 | 2024-10-30 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J3124 | 2022-09-14 | Active | Not Started | Saginaw |  | Murphy 345 kV Substation | 120 | Solar | DPP-2022 Phase 2 | 2026-08-31 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J1389 | 2019-04-29 | Done | Not Started | Saginaw County | METC | Murphy Station - Nelson Road 345 kV Line tap | 120 | Solar | DPP-2019 GIA | 2022-08-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J2374 | 2022-09-15 | Active | Not Started | Sanilac | ITC | J1557 Sub | 200 | Solar | DPP-2022 Phase 2 | 2025-06-30 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J1944 | 2021-08-23 | Active | Not Started | Sanilac | ITC | GREENWOOD - RAPSON (BANNER) 345.0kV | 185 | Solar | DPP-2021 Phase 3 | 2023-11-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J3633 | 2024-04-13 | Active |  | Sanilac | ITC | GREENWOOD - RAPSON (BANNER) 345.0kV | 200 | Solar | DPP-2023 Phase 2 | 2028-09-15 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J1196 | 2019-04-25 | Done | Not Started | Sanilac County | ITC MIDWEST | Greenwood - Rapson (Banner) 345 kV Line Tap | 200 | Solar | DPP-2019 GIA | 2022-08-29 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J2672 | 2022-09-14 | Active | Not Started | Shiawassee | METC | BINGHAM - CORNELL 138.0kV | 120 | Solar | DPP-2022 Phase 2 | 2025-11-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J1297 | 2019-04-29 | Done | Under Construction | Shiawassee County | METC | Cornell - Bell Road 138 kV Line | 170 | Solar | DPP-2019 GIA | 2021-12-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J796 | 2017-06-16 | Done | In Service | Shiawassee County | METC | Goss 138kV Substation | 239 | Solar | DPP-2017-AUG GIA | 2019-09-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J1664 | 2020-06-24 | Done | Not Started | St. Clair | ITC | Carrigan 120kV Substation | 200 | Solar | DPP-2020 GIA | 2023-09-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J2677 | 2022-09-14 | Active | Not Started | St. Clair | ITC | Greenwood 120 kV | 195 | Solar | DPP-2022 Phase 2 | 2025-11-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J1331 | 2019-04-29 | Done | Not Started | St. Clair County | ITC | Greenwood 120 kV Substation | 100 | Solar | DPP-2019 GIA | 2022-06-30 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J3844 | 2024-11-26 | Active |  | St. Joseph | METC | BATAVIA - MORROW 138.0kV | 150 | Solar | DPP-2025 Phase 1 | 2029-04-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J3908 | 2025-03-10 | Active |  | St. Joseph | METC | BATAVIA - MORROW 138.0kV | 196 | Solar | DPP-2026 | 2025-04-30 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J2490 | 2022-09-14 | Active | Not Started | Tuscola | ITC | Tuscola-Arrowhead 120kV Transmission Line | 125 | Solar | DPP-2022 Phase 2 | 2025-11-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J2578 | 2022-09-13 | Active | Not Started | Tuscola | METC | KARN - THETFORD (ATLANTA) 138.0kV | 180 | Solar | DPP-2022 Phase 2 | 2026-09-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J3837 | 2024-12-02 | Active |  | Van Buren | METC | ARGENTA - PALISADES 345.0kV | 200 | Solar | DPP-2025 Phase 1 | 2029-06-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J2444 | 2022-09-14 | Active | Not Started | Van Buren | METC | ARGENTA - TWIN BRANCH 345.0kV | 220 | Solar | DPP-2022 Phase 2 | 2026-08-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J3653 | 2024-04-05 | Active |  | Washtenaw | ITC | Line tap on Superior-Wayne 120kV line at 42.275480, -83.628250 | 80 | Solar | DPP-2023 Phase 2 | 2028-06-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J3945 | 2025-04-07 | Active |  | Washtenaw | ITC | MAJESTIC - MILAN 345.0kV | 245 | Solar | DPP-2026 | 2030-01-31 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J1062 | 2018-03-12 | Done | Not Started | Washtenaw County | ITC MIDWEST | Majestic - Lemoyne 345 kV Line Tap | 200 | Solar | DPP-2018-APR GIA | 2021-10-31 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J1224 | 2019-04-27 | Done | Under Construction | Washtenaw County | ITC MIDWEST | Majestic - Milan 345 kV Line Tap | 170 | Solar | DPP-2019 GIA | 2022-10-30 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J799 | 2017-06-16 | Done | Under Construction | Washtenaw County | ITC MIDWEST | Milan - Pioneer 120kV Line Tap | 189 | Solar | DPP-2017-AUG GIA | 2019-09-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)
J3723 | 2024-04-15 | Active |  | Wexford | METC | KEYSTONE - LUDINGTON 345.0kV | 300 | Solar | DPP-2023 Phase 2 | 2028-09-01 | https://www.misoenergy.org/api/giqueue/getprojects (pulled 2026-10-20)